## Sheet1
CSI4142 - Project 2022
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Create database instance | Omer | 2022-02-22 | 2022-02-22 | 0.5 | 1 | We used our student azure credits to make a database
Create event dimension | Sammy | 2022-03-03 | 2022-03-06 | 0.5 | 3.5 | This includes time spent manually searching for events to add via Wikipedia and the News
Create country dimension | Anthony | 2022-03-03 | 2022-03-06 | 0.5 | 1
Create education dimension | Omer | 2022-03-03 | 2022-03-06 | 0.5 | 1
Create health dimension | Anthony | 2022-03-03 | 2022-03-06 | 0.5 | 1
Create month dimension | Anthony | 2022-03-03 | 2022-03-06 | 0.5 | 1
Create nutrition dimension | Sammy | 2022-03-03 | 2022-03-14 | 0.5 | 1
Create population dimension | Anthony | 2022-03-03 | 2022-03-06 | 0.5 | 1
Create quality of life dimension | Omer | 2022-03-03 | 2022-03-06 | 0.5 | 1
Staging of dimension event | Omer | 2022-03-14 | 2022-03-14 | 0.5 | 0.5
Staging of dimension nutrition | Sammy | 2022-03-14 | 2022-03-14 | 1 | 1 | For staging, we wrote a pipeline that could automatically stage every dimension for us giving a pre-processed csv
Staging of country dimension | Anthony | 2022-03-14 | 2022-03-14 | 1 | 1
Staging of education dimension | Omer | 2022-03-14 | 2022-03-14 | 1 | 1
Staging of health dimension | Anthony | 2022-03-14 | 2022-03-14 | 1 | 1
Staging of month dimension | Anthony | 2022-03-14 | 2022-03-14 | 1 | 1
Staging population dimension | Anthony | 2022-03-14 | 2022-03-14 | 1 | 1
Staging quality of life dimension | Omer | 2022-03-14 | 2022-03-14 | 1 | 1
Surrogate key pipeline | Anthony, Sammy | 2022-03-14 | 2022-03-14 | 2 | 1
Staging of fact table – including FKs and measures | Anthony Sammy, Omer | 2022-03-14 | 2022-03-14 | 1 | 2
Data quality handling and reporting | Anthony, Sammy, Omer | 2022-03-14 | 2022-03-14 | 2 | 2 | Everyone handled data quality issue for their own dimension